## Weekly Tracker
🚀 SUSHANTH'S AI/GenAI ENGINEER ROADMAP — 26-WEEK TRACKER
✅ PRE-WEEK 0 COMPLETE: Karpathy 'Let's Build GPT from Scratch' — nanoGPT, self-attention, multi-head, residuals, layer norm, full GPT assembled
Week | Phase | Track | Course / Resource | Key Topics | Deliverable | Learn Hrs | Build Hrs | Resource 1 | Resource 2 | Resource 3 | Notes | Status
1 | Phase 1 | GenAI | Ed Donner Wk 1 + Illustrated Transformer | Transformer architecture, tokenization, context window, embeddings overview | Blog post: 'How transformers work — in my own words' | 2 | 1 | jalammar.github.io/illustrated-transformer | Ed Donner Udemy Course | 3Blue1Brown Neural Nets | In Progress | In Progress
2 | Phase 1 | GenAI | Ed Donner Wk 2 — LLM APIs | OpenAI + Anthropic APIs, structured outputs (Pydantic/instructor), tool calling | Working script: multi-provider API wrapper with streaming | 2 | 2 | OpenAI API Docs | Anthropic API Docs | instructor library |  | Not Started
3 | Phase 1 | GenAI | Ed Donner Wk 3 — Local LLMs + FastAPI | Ollama setup, FastAPI streaming endpoint, REST API design for AI | FastAPI endpoint: /chat with SSE streaming + Ollama local backend | 2 | 3 | Ollama Docs | FastAPI Docs | LiteLLM multi-provider |  | Not Started
4 | Phase 1 | Project | Ed Donner Wk 4 — Ship Chatbot | Multi-turn chat, session memory (last 20 turns), React SSE consumer, deploy Railway | 🚀 P1: Multi-turn Chatbot LIVE on Railway | 1 | 4 | Railway Deploy | Vercel Frontend | React SSE guide |  | Not Started
5 | Phase 2 | RAG | Ed Donner Wk 5 — Embeddings + Vector DBs | Cosine similarity, embedding models comparison, Chroma vs Pinecone, ANN algorithms | Notebook: embed 100 docs → query with semantic search → compare results | 2 | 2 | Pinecone Docs | Chroma Docs | voyage-code-2 embeddings |  | Not Started
6 | Phase 2 | RAG | Ed Donner Wk 6 — RAG Pipeline + LangChain LCEL | Chunking strategies, HyDE, hybrid search, reranking, LCEL pipe syntax | Working RAG pipeline: PDF → chunk → embed → Pinecone → query with citations | 2 | 3 | LangChain LCEL Docs | RAG chunking guide | LangSmith tracing | Tip: bias use case toward firmware/security docs if possible | Not Started
7 | Phase 2 | RAG | Ed Donner Wk 7 — Evaluation | RAGAS metrics (faithfulness, context recall), Promptfoo, build eval harness | Eval suite: 20-question test set, RAGAS scores baseline vs improved pipeline | 2 | 2 | RAGAS Docs | Promptfoo | LangSmith eval |  | Not Started
8 | Phase 2 | Project | Ed Donner Wk 8 — Ship RAG App | PyMuPDF ingestion, namespace by doc_id, parent-child chunking, full RAGAS eval | 🚀 P2: Document Q&A RAG App LIVE — with citation UI + RAGAS score in README | 1 | 4 | PyMuPDF Docs | RAGAS GitHub | Pinecone quickstart | Consider: BIOS/firmware spec docs as dataset for niche differentiation | Not Started
9 | Phase 2 | RAG | Ed Donner Wk 9 — LlamaIndex | LlamaIndex core: nodes, indices, query engines, LangChain vs LlamaIndex comparison | Side-by-side: same RAG pipeline in LangChain vs LlamaIndex — notes on tradeoffs | 2 | 2 | LlamaIndex Docs | LlamaIndex vs LangChain | LlamaIndex starter |  | Not Started
10 | Phase 2 | Career | OSS Contribution #1 (docs/tests) | First open source PR — LangChain or RAGAS docs fix or test addition | Merged PR on LangChain/RAGAS — add to GitHub profile + LinkedIn post | 1 | 2 | goodfirstissue.dev | LangChain GitHub | RAGAS GitHub |  | Not Started
11 | Phase 3 | Agents | LangGraph Course Wk 1 — Agent Patterns | ReAct loop, custom tools, chains vs agents decision, failure modes | Custom tool-calling agent: 3 tools (web search, calculator, code runner) | 2 | 2 | LangGraph Course Udemy | ReAct paper | LangChain tools docs |  | Not Started
12 | Phase 3 | Agents | LangGraph Course Wk 2 — LangGraph | StateGraph, nodes, edges, conditional routing, human-in-the-loop, MemorySaver | LangGraph workflow: 3-node graph with conditional edges + interrupt for approval | 2 | 3 | LangGraph Docs | LangGraph tutorials | LangGraph MCP guide |  | Not Started
13 | Phase 3 | Agents | LangGraph Course Wk 3 — Multi-Agent | CrewAI, supervisor patterns, cost control, multi-agent orchestration | 🚀 P3: Test Generator Agent — LangGraph + PyGitHub + Claude Sonnet + auto-PR | 1 | 4 | CrewAI Docs | LangGraph multi-agent | PyGitHub Docs |  | Not Started
14 | Phase 3 | GenAI | Ed Donner Wk 8 (fine-tuning module) — Fine-tuning | LoRA math, QLoRA, when to fine-tune vs RAG, training data formats (JSONL), Unsloth | Fine-tuned model on HuggingFace Hub — model card with eval metrics | 3 | 2 | Unsloth QLoRA | HuggingFace PEFT | LoRA paper |  | Not Started
15 | Phase 3 | Career | Resume + LinkedIn + Interview Prep | Resume updated with all projects, LinkedIn About rewrite, RAGAS/agent interview Qs | Updated resume live, LinkedIn 500+ connections, 10 applications sent to Tier 2 | 2 | 1 | JobScan ATS checker | AI interview questions | LinkedIn optimization | Tier 2 targets: Sarvam AI, Krutrim, Portkey, Glean, Qualcomm AI, ARM | Not Started
16 | Phase 3 | Career | OSS Contribution #2 (bug fix) | Medium-difficulty bug fix in LangChain/LiteLLM/LlamaIndex | Merged bug-fix PR — blog post: 'What I learned contributing to LangChain' | 1 | 2 | LiteLLM GitHub | LlamaIndex issues | LangGraph issues |  | Not Started
17 | Phase 4 | Project | Capstone: Architecture + tree-sitter | tree-sitter vs ast, AST function extraction, code embedding strategy design | tree-sitter parser: extract all functions from Python/JS repo with type hints | 2 | 3 | tree-sitter Docs | voyage-code-2 | AST explorer |  | Not Started
18 | Phase 4 | Project | Capstone: RAG + Review Engine | Codebase RAG: index functions, retrieve similar patterns, context-aware review | Core review engine: submit file → get structured review with line citations | 1 | 4 | Click CLI docs | Rich library | Pydantic structured outputs |  | Not Started
19 | Phase 4 | Project | Capstone: CLI + Eval Harness | Click + Rich CLI polish, 50-case eval harness (precision/recall/P95 latency) | CLI v1 published on PyPI (test index) — eval harness green on all 50 cases | 1 | 4 | PyPI packaging guide | Pytest docs | twine upload |  | Not Started
20 | Phase 4 | Project | Capstone: VS Code Extension | VS Code extension TypeScript template, webview panel, Language Server basics | VS Code extension: right-click → Review with AI — calls local FastAPI backend | 1 | 4 | VS Code extension guide | VS Code webview API | TypeScript docs |  | Not Started
21 | Phase 4 | Career | OSS Contribution #3 + HF Space | New integration PR (LangChain/Promptfoo), publish HF Space demo of capstone | HF Space live, OSS PR merged, HuggingFace model card published | 1 | 3 | HuggingFace Spaces | Gradio docs | HF model card guide |  | Not Started
22 | Phase 4 | Project | Capstone: Ship + Blog | Production deploy Railway, README with GIF + metrics + decision document, launch LinkedIn post | 🚀 P4: AI Coding Assistant LIVE — PyPI + VS Code + HF Space + blog post | 1 | 4 | Railway deploy | shields.io badges | Carbon code screenshots | Every README must have: why this tool, where it fails, what you'd monitor | Not Started
23 | Phase 5 | Career | System Design Interview Prep | 45-min RAG system design answer, LLM observability, cost control patterns | Mock interview: 45-min RAG design recorded + self-reviewed | 3 | 1 | Designing ML Systems book | AI system design guide | LLM cost calculator |  | Not Started
24 | Phase 5 | Career | Active Applying — Tier 2 + Tier 1 | Tailored resume per company, referral outreach, technical screen prep | 20 applications sent, 5 referrals requested, 3 technical screens scheduled | 1 | 0 | Wellfound AI jobs | Otta jobs | LinkedIn Easy Apply | Tier 1 (FAANG) apply Week 24+ only. Tier 2 already in progress from Week 15 | Not Started
25 | Phase 5 | Career | Interview Execution | DSA + LLM fundamentals + RAG + agent + system design — all tracks | All scheduled interviews completed — track outcomes in Company Targets sheet | 3 | 0 | NeetCode DSA | AI interview questions | Pramp mock interviews |  | Not Started
26 | Phase 5 | Career | Offer Evaluation + Negotiation | Salary benchmarking, ESOP evaluation, negotiation scripts | ✅ SIGNED OFFER — ≥ ₹24 LPA target | 1 | 0 | Levels.fyi India salaries | Glassdoor salaries | Negotiation guide |  | Not Started

## Course Map
📚 COURSE MAP — What to Study, When, and How
# | Course / Resource | Instructor | Platform | Plan Weeks | Cost | How to Use | URL / Link
1 | LLM Engineering: Master AI, Large Language Models & Agents | Ed Donner | Udemy | Wks 1–4 (Foundation) + Wks 5–9 (RAG) + Wk 14 (Fine-tuning) | ₹499–699 on sale | PRIMARY backbone. Follow sequentially. Use his code as reference — build YOUR projects, don't copy along. Do NOT pay full price — wait for Udemy sale. | udemy.com/course/llm-engineering-master-ai-and-large-language-models/
2 | Develop AI Agents with LangChain & LangGraph | (Udemy) | Udemy | Wks 11–13 (Agents) | ₹499–699 on sale | Covers LangChain V1.2+, LangGraph, MCP integration, production agentic systems. Use for P3 Test Generator Agent. | Search 'LangGraph LangChain agents Udemy'
3 | NLP Course | HuggingFace | huggingface.co (FREE) | Wks 1–4 supplement | Free | Weekend reading supplement. Covers tokenizers, HF Transformers library, pipelines. Don't replace Ed Donner with this — supplement only. | huggingface.co/learn/nlp-course
4 | Generative AI for Beginners (18 lessons) | Microsoft | GitHub (FREE) | Wks 1–3 weekend reading | Free | 18 lessons. Weekend reading only, not a primary track. Skim for context, don't do all exercises. | github.com/microsoft/generative-ai-for-beginners
5 | HuggingFace Agents Course — Unit 2 ONLY (smolagents) | HuggingFace | huggingface.co (FREE) | Wk 11–13 alongside LangGraph | Free | ⚠️ Do Unit 2 (smolagents) ONLY. Rest is redundant given LangGraph course. Skip Units 1, 3, 4. | huggingface.co/learn/agents-course
6 | Zero to Hero / nanoGPT (Karpathy) | Andrej Karpathy | YouTube (FREE) | ✅ COMPLETED pre-Week 1 | Free | DONE. Covered: BigramLM → self-attention → multi-head → feedforward → residuals → layer norm → full GPT. No further action needed. | youtube.com/@AndrejKarpathy

## Project Milestones
🏗️ PROJECT MILESTONES — Build Tracker
Project | Week | Stack / Tools | Key Metric / Success Criteria | Deploy Target | Decision Document? | Status | Notes
P0 — nanoGPT (Karpathy) | Pre-Wk 1 | PyTorch, nn.Module, self-attention | Understand full GPT architecture end-to-end — loss ~1.48 Shakespeare generation | Local only | N/A (learning project) | ✅ Done | Covers: BigramLM → multi-head → FF → residuals → LayerNorm → full GPT
P1 — Multi-turn Chatbot | Week 4 | React + FastAPI + AsyncOpenAI + SSE streaming | Live URL, <500ms first token, session memory 20 turns, streaming visible | Railway (API) + Vercel (Frontend) | No — ship first project | Not Started | First public project. Start LinkedIn posting from this week.
P2 — Document Q&A RAG App | Week 8 | PyMuPDF + Pinecone + RAGAS + LangChain LCEL | RAGAS faithfulness > 0.85, citation UI shows source chunk, README has eval scores | Railway + HuggingFace Space | Yes — chunking strategy decision doc | Not Started | Niche tip: consider BIOS/firmware specs or security docs as dataset. Instant differentiator vs generic chatbot.
P3 — Test Generator Agent | Week 13 | LangGraph + PyGitHub + Claude Sonnet API | Agent reads PR diff → generates JUnit test → opens auto-PR. End-to-end working. | GitHub Actions + Railway | Yes — why LangGraph over CrewAI | Not Started | Directly maps to Intel validation background. Strong resume signal.
P3b — Fine-tuned Model | Week 14 | QLoRA + Unsloth + HuggingFace PEFT | Model card published: eval metrics, training data description, limitations section | HuggingFace Hub | Yes — fine-tune vs RAG decision doc | Not Started
P4 — AI Coding Assistant (Capstone) | Weeks 17–22 | tree-sitter + voyage-code-2 + Claude Sonnet + FastAPI + Click/Rich + TypeScript VS Code ext | 50-case eval harness green. P95 latency <2s. PyPI installable. VS Code extension published. | Railway (API) + PyPI (CLI) + VS Code Marketplace + HF Space | Yes — every technical decision documented | Not Started | Interview pitch: 45-second scripted answer. Every sentence = tech decision + reason.

## 6-Month Overview
📊 6-MONTH OVERVIEW — Phases, Goals & Salary Targets
Phase | Weeks | Theme | Key Topics | Capstone / Deliverable | Course
Phase 1 | Weeks 1–4 | Foundation | Transformer theory → LLM APIs (OpenAI + Anthropic) → Prompt engineering → HuggingFace → FastAPI → Local LLMs (Ollama) | P1: Multi-turn Chatbot LIVE on Railway | Ed Donner Wks 1–4
Phase 2 | Weeks 5–10 | RAG | Embeddings → Vector DBs (Chroma + Pinecone) → RAG pipelines → LangChain LCEL → RAGAS evals → LlamaIndex → OSS Contribution #1 | P2: Document Q&A RAG App — RAGAS faithfulness > 0.85, citation UI | Ed Donner Wks 5–9
Phase 3 | Weeks 11–16 | Agents + Fine-tuning | Agent patterns (ReAct) → LangGraph → Multi-agent (CrewAI) → QLoRA fine-tuning → Resume overhaul → OSS Contribution #2 | P3: Test Generator Agent + P3b: LoRA model on HF Hub | LangGraph Udemy + Ed Donner fine-tuning
Phase 4 | Weeks 17–22 | Capstone Build | tree-sitter → Code embeddings → CLI (Click + Rich) → VS Code extension → 50-case eval harness → Ship to PyPI + Marketplace | P4: AI Coding Assistant — PyPI + VS Code Marketplace + HF Space + Railway | No course — original build
Phase 5 | Weeks 23–26 | Job Hunt | System design prep → Active applying Tier 2 (already started Wk 15) → Tier 1 → Interview execution → Offer evaluation | ✅ SIGNED OFFER ≥ ₹24 LPA | N/A
💰 SALARY TARGETS
Target | Amount | Timeline
At Switch | ≥ ₹24 LPA | Week 26 (end of plan)
18 Months Post-Switch | ₹30–40 LPA | 18 months after joining
Current (Intel) | ₹18.5 LPA | Now

## Company Targets
🎯 COMPANY TARGETS — Apply Timeline & Strategy
Tier | Company | Location | Apply Week | Why You Fit | Careers Link | Status
Tier 2 🔥 | Sarvam AI | Bengaluru | Week 15 | India's leading LLM company. Builds Indian language models. Cares about what you've BUILT not LC grinding. RAG + agents stack is perfect. | sarvam.ai/careers | Not Applied
Tier 2 🔥 | Krutrim | Bengaluru | Week 15 | Ola's AI lab. Fast-moving. India-focused LLM. Your Intel Bengaluru background + AI stack is a direct fit. | krutrim.com/careers | Not Applied
Tier 2 | Portkey.ai | Remote/Bengaluru | Week 15 | LLM gateway / observability tooling. Your LiteLLM + cost tracking knowledge from capstone directly relevant. | portkey.ai/careers | Not Applied
Tier 2 | Glean | Bengaluru (India eng) | Week 15 | Enterprise search + RAG at scale. Strong RAG pipeline + embedding experience needed. P2 RAG app is direct proof. | glean.com/careers | Not Applied
Tier 2 | Writer AI | Remote | Week 16 | Enterprise GenAI platform. Values full-stack AI engineering. | writer.com/careers | Not Applied
Tier 2 | Cohere | Remote | Week 16 | LLM API company. Strong ML/NLP culture. Good for someone with federated learning + fine-tuning background. | cohere.com/careers | Not Applied
Tier 2 (Intel leverage) | Qualcomm AI | Bengaluru/Hyderabad | Week 16 | Your Intel hardware + firmware background + AI skills = rare combo they value. AI inference on-device work. | qualcomm.com/careers | Not Applied
Tier 2 (Intel leverage) | ARM | Bengaluru | Week 16 | ML for edge/embedded systems. Intel validation background is directly transferable. | arm.com/careers | Not Applied
Tier 2 (Security AI) | CrowdStrike (India) | Bengaluru | Week 18 | AI + cybersecurity. Your IFWI/security exposure from Intel team + AI skills = niche intersection. | crowdstrike.com/careers | Not Applied
Tier 2 (Security AI) | Palo Alto Networks AI | Bengaluru | Week 18 | AI-powered threat detection. Security domain knowledge from Intel IFWI team is differentiator. | paloaltonetworks.com/careers | Not Applied
Tier 3 | Wellfound (AngelList) | Remote/Bengaluru | Week 14 onwards | AI-filtered job board. Set up alerts: 'LLM Engineer', 'GenAI Engineer', 'RAG'. Apply continuously. | wellfound.com | Ongoing
Tier 3 | LinkedIn AI Filter | Remote/Bengaluru | Week 14 onwards | Filter: AI Engineering roles, Bengaluru + Remote. Easy Apply where available. | linkedin.com/jobs | Ongoing
Tier 3 | Otta | Remote | Week 14 onwards | Strong for startup AI roles. Good signal-to-noise vs LinkedIn. | otta.com | Ongoing
Tier 1 (Week 24+) | Google DeepMind India | Bengaluru | Week 24 | Requires strong LC + system design. Apply only after Week 24 prep. | deepmind.google/careers | Not Applied
Tier 1 (Week 24+) | Microsoft AI (India) | Hyderabad/Bengaluru | Week 24 | Azure AI + Copilot teams. Strong FastAPI + LangChain + OSS contributions needed. | microsoft.com/careers | Not Applied
Tier 1 (Week 24+) | Meta AI | Bengaluru | Week 24 | LLaMA team, applied AI research. Strong LC + systems background required. | metacareers.com | Not Applied

## Visibility Strategy
📣 VISIBILITY STRATEGY — LinkedIn · GitHub · HuggingFace · OSS · Hackathons
LinkedIn
| Start posting | Week 4 (when P1 ships). Not before — you need something to show.
| Post hook formula | RESULT FIRST: 'Reduced RAG hallucination 40% by...' NOT 'I learned X today'
| 5 post types | Build log ¦ Lesson learned ¦ Comparison (LangChain vs LlamaIndex) ¦ OSS contribution ¦ Resource share
| Connection strategy | 5 engineers/week from Week 6. Comment before DM. Never lead with job-seeking.
| Open to Work | Enable for RECRUITERS ONLY (not public banner) at Week 22
| Week 22 headline | AI/LLM Engineer ¦ RAG · Agents · FastAPI ¦ Intel ¦ Open to Opportunities
| Ayush Singh insight | Confusion is content. Mistakes are content. Write authentically — what broke, how you fixed it.
GitHub
| Commit frequency | Minimum 5 commits/week. Commit message quality matters.
| 6 pinned repos (order) | Coding Assistant → RAG App → Test Generator Agent → Chatbot → Federated Learning → LeetCode
| Every repo must have | Live URL or GIF demo ¦ Eval metrics ¦ Architecture diagram ¦ Decision document section
| Decision doc format | Why this tool? Where would it fail? What would you monitor in production?
HuggingFace
| Week 14 | Publish fine-tuned model + full model card (eval metrics, training data, limitations)
| Week 21 | HF Space demo of capstone (Gradio UI)
OSS Contributions
| Week 10 | Docs/tests PR — LangChain or RAGAS (low friction first PR)
| Week 16 | Bug fix — LiteLLM or LlamaIndex (medium difficulty)
| Week 21 | New integration — LangChain or Promptfoo
| Priority order | LangChain > RAGAS > LlamaIndex > LiteLLM > LangGraph > Promptfoo
| Find issues | goodfirstissue.dev/language/python
Hackathons
| Month 3 | Lablab.ai
| Month 4 | HuggingFace Sprint
| Month 5 | Anthropic/Meta hackathon
| Playbook | Working demo by hour 8. Polish hours 8–20. Submit hours 20–24. Demo > polish.
Communities + X
| Discord | LangChain: discord.gg/langchain ¦ HuggingFace: discord.gg/huggingface ¦ 10 min/day
| India communities | TFUG Bengaluru ¦ PyData Bengaluru ¦ IndiaAI community
| X — global signal | @karpathy @ylecun @AlphaSignalAI @weights_biases @LangChainAI @AnthropicAI @huggingface
| X — India market | @sarvam_ai @BangaloreAI @iSPIRT @krishnanrohit
| Rule | Answer questions you know. Never post job-seeking in technical channels.