## Weekly Tracker
🚀 SUSHANTH'S AI/GenAI ENGINEER ROADMAP — 26-WEEK TRACKER
Week | Phase | Track | Course / Resource | Key Topics | Deliverable | Learn Hrs | Build Hrs | Resource 1 | Resource 2 | Resource 3 | Status
1 | Phase 1 | GenAI | Ed Donner Wk 1 + Illustrated Transformer | Transformer architecture, tokenization, context window, embeddings overview | Blog post: 'How transformers work — in my own words' | 2 | 1 | Illustrated Transformer | Ed Donner Udemy Course | 3Blue1Brown Neural Nets | Not Started
2 | Phase 1 | GenAI | Ed Donner Wk 2 — LLM APIs | OpenAI + Anthropic APIs, structured outputs (Pydantic/instructor), tool calling | Working script: multi-provider API wrapper with streaming | 2 | 2 | OpenAI API Docs | Anthropic API Docs | instructor library | Not Started
3 | Phase 1 | GenAI | Ed Donner Wk 3 — Local LLMs + FastAPI | Ollama setup, FastAPI streaming endpoint, REST API design for AI | FastAPI endpoint: /chat with SSE streaming + Ollama local backend | 2 | 3 | Ollama Docs | FastAPI Docs | LiteLLM multi-provider | Not Started
4 | Phase 1 | Project | Ed Donner Wk 4 — Ship Chatbot | Multi-turn chat, session memory (last 20 turns), React SSE consumer, deploy Railway | 🚀 P1: Multi-turn Chatbot LIVE on Railway | 1 | 4 | Railway Deploy | Vercel Frontend | React SSE guide | Not Started
5 | Phase 2 | RAG | Ed Donner Wk 5 — Embeddings + Vector DBs | Cosine similarity, embedding models comparison, Chroma vs Pinecone, ANN algorithms | Notebook: embed 100 docs → query with semantic search → compare results | 2 | 2 | Pinecone Docs | Chroma Docs | voyage-code-2 embeddings | Not Started
6 | Phase 2 | RAG | Ed Donner Wk 6 — RAG Pipeline + LangChain LCEL | Chunking strategies, HyDE, hybrid search, reranking, LCEL pipe syntax | Working RAG pipeline: PDF → chunk → embed → Pinecone → query with citations | 2 | 3 | LangChain LCEL Docs | RAG chunking guide | LangSmith tracing | Not Started
7 | Phase 2 | RAG | Ed Donner Wk 7 — Evaluation | RAGAS metrics (faithfulness, context recall), Promptfoo, build eval harness | Eval suite: 20-question test set, RAGAS scores baseline vs improved pipeline | 2 | 2 | RAGAS Docs | Promptfoo | LangSmith eval | Not Started
8 | Phase 2 | Project | Ed Donner Wk 8 — Ship RAG App | PyMuPDF ingestion, namespace by doc_id, parent-child chunking, full RAGAS eval | 🚀 P2: Document Q&A RAG App LIVE — with citation UI + RAGAS score in README | 1 | 4 | PyMuPDF Docs | RAGAS GitHub | Pinecone quickstart | Not Started
9 | Phase 2 | RAG | Ed Donner Wk 9 — LlamaIndex | LlamaIndex core: nodes, indices, query engines, LangChain vs LlamaIndex comparison | Side-by-side: same RAG pipeline in LangChain vs LlamaIndex — notes on tradeoffs | 2 | 2 | LlamaIndex Docs | LlamaIndex vs LangChain | LlamaIndex starter | Not Started
10 | Phase 2 | Career | OSS Contribution #1 (docs/tests) | First open source PR — LangChain or RAGAS docs fix or test addition | Merged PR on LangChain/RAGAS — add to GitHub profile + LinkedIn post | 1 | 2 | goodfirstissue.dev | LangChain GitHub | RAGAS GitHub | Not Started
11 | Phase 3 | Agents | LangGraph Course Wk 1 — Agent Patterns | ReAct loop, custom tools, chains vs agents decision, failure modes | Custom tool-calling agent: 3 tools (web search, calculator, code runner) | 2 | 2 | LangGraph Course Udemy | ReAct paper | LangChain tools docs | Not Started
12 | Phase 3 | Agents | LangGraph Course Wk 2 — LangGraph | StateGraph, nodes, edges, conditional routing, human-in-the-loop, MemorySaver | LangGraph workflow: 3-node graph with conditional edges + interrupt for approval | 2 | 3 | LangGraph Docs | LangGraph tutorials | LangGraph MCP guide | Not Started
13 | Phase 3 | Agents | LangGraph Course Wk 3 — Multi-Agent | CrewAI, supervisor patterns, cost control, multi-agent orchestration | 🚀 P3: Test Generator Agent — LangGraph + PyGitHub + Claude Sonnet + auto-PR | 1 | 4 | CrewAI Docs | LangGraph multi-agent | PyGitHub Docs | Not Started
14 | Phase 3 | GenAI | LangGraph Course Wk 4 — Fine-tuning | LoRA math, QLoRA, when to fine-tune vs RAG, training data formats (JSONL), Unsloth | Fine-tuned model on HuggingFace Hub — model card with eval metrics | 3 | 2 | Unsloth QLoRA | HuggingFace PEFT | LoRA paper | Not Started
15 | Phase 3 | Career | Resume + LinkedIn + Interview Prep | Resume updated with all projects, LinkedIn About rewrite, RAGAS/agent interview Qs | Updated resume live, LinkedIn 500+ connections, 10 applications sent to Tier 2 | 2 | 1 | JobScan ATS checker | AI interview questions | LinkedIn optimization | Not Started
16 | Phase 3 | Career | OSS Contribution #2 (bug fix) | Medium-difficulty bug fix in LangChain/LiteLLM/LlamaIndex | Merged bug-fix PR — blog post: 'What I learned contributing to LangChain' | 1 | 2 | LiteLLM GitHub | LlamaIndex issues | LangGraph issues | Not Started
17 | Phase 4 | Project | Capstone: Architecture + tree-sitter | tree-sitter vs ast, AST function extraction, code embedding strategy design | tree-sitter parser: extract all functions from Python/JS repo with type hints | 2 | 3 | tree-sitter Docs | voyage-code-2 | AST explorer | Not Started
18 | Phase 4 | Project | Capstone: RAG + Review Engine | Codebase RAG: index functions, retrieve similar patterns, context-aware review | Core review engine: submit file → get structured review with line citations | 1 | 4 | Click CLI docs | Rich library | Pydantic structured outputs | Not Started
19 | Phase 4 | Project | Capstone: CLI + Eval Harness | Click + Rich CLI polish, 50-case eval harness (precision/recall/P95 latency) | CLI v1 published on PyPI (test index) — eval harness green on all 50 cases | 1 | 4 | PyPI packaging guide | Pytest docs | twine upload | Not Started
20 | Phase 4 | Project | Capstone: VS Code Extension | VS Code extension TypeScript template, webview panel, Language Server basics | VS Code extension: right-click → Review with AI — calls local FastAPI backend | 1 | 4 | VS Code extension guide | VS Code webview API | TypeScript docs | Not Started
21 | Phase 4 | Career | OSS Contribution #3 + HF Space | New integration PR (LangChain/Promptfoo), publish HF Space demo of capstone | HF Space live, OSS PR merged, HuggingFace model card published | 1 | 3 | HuggingFace Spaces | Gradio docs | HF model card guide | Not Started
22 | Phase 4 | Project | Capstone: Ship + Blog | Production deploy Railway, README with GIF + metrics, launch LinkedIn post | 🚀 P4: AI Coding Assistant LIVE — PyPI + VS Code + HF Space + blog post | 1 | 4 | Railway deploy | shields.io badges | Carbon code screenshots | Not Started
23 | Phase 5 | Career | System Design Interview Prep | 45-min RAG system design answer, LLM observability, cost control patterns | Mock interview: 45-min RAG design recorded + self-reviewed | 3 | 1 | Designing ML Systems book | AI system design guide | LLM cost calculator | Not Started
24 | Phase 5 | Career | Active Applying — Tier 1 + 2 | Tailored resume per company, referral outreach, technical screen prep | 20 applications sent, 5 referrals requested, 3 technical screens scheduled | 1 | 0 | Wellfound AI jobs | Otta jobs | LinkedIn Easy Apply | Not Started
25 | Phase 5 | Career | Interview Execution | DSA + LLM fundamentals + RAG + agent + system design — all tracks | All scheduled interviews completed — track outcomes in Company Targets sheet | 3 | 0 | NeetCode DSA | AI interview questions | Pramp mock interviews | Not Started
26 | Phase 5 | Career | Offer Evaluation + Negotiation | Salary benchmarking, ESOP evaluation, negotiation scripts | ✅ SIGNED OFFER — ≥ ₹24 LPA target | 1 | 0 | Levels.fyi India salaries | Glassdoor salaries | Negotiation guide | Not Started

## Course Map
📚 STRUCTURED COURSE BACKBONE
Course | Platform | Weeks | Cost | URL | What It Covers | How To Use
LLM Engineering: Master AI, Large Language Models & Agents | Udemy | 1–16 | ₹499–699 | 🔗 Open | LLM APIs, RAG, agents, QLoRA fine-tuning, 8 real projects. Ed Donner (ex-AI startup founder). | PRIMARY backbone for Phases 1–3. Follow sequentially. Build YOUR projects using his code as reference — don't just copy along.
Develop AI Agents with LangChain & LangGraph | Udemy | 11–13 | ₹499–699 | 🔗 Open | LangChain V1.2+, LangGraph stateful graphs, MCP integration, production agentic systems. | Jump to this for Weeks 11-13 agent phase. Covers the exact LangGraph patterns needed for P3 Test Generator Agent.
HuggingFace Transformers Course (free) | HuggingFace | 1–4 | Free | 🔗 Open | Transformers, tokenizers, fine-tuning, HF Hub, datasets, pipelines. | Supplement Ed Donner Wks 1-2. Great reference when working with HF models. Free and self-paced.
HuggingFace Agents Course (free — Unit 2 only) | HuggingFace | 11–13 | Free | 🔗 Open | smolagents (HF's lightweight agent framework), LangGraph, LlamaIndex agents. | Only do Unit 2 (smolagents section). Adds HF-native agent tool to your kit alongside LangGraph. Skip rest — covered by Udemy course.
Generative AI for Beginners — Microsoft (free) | GitHub/Microsoft | 1–3 | Free | 🔗 Open | 18 lessons: LLM fundamentals → prompt engineering → RAG → agents. Well maintained. | Use as weekend reading during Weeks 1-3 to reinforce Ed Donner. Good for filling gaps.
Andrej Karpathy — Zero to Hero playlist | YouTube | Pre-Week 1 | Free | 🔗 Open | makemore (bigram → MLP → RNN → attention), nanoGPT from scratch, tokenizer from scratch. | You are HERE. Finish nanoGPT video this weekend. These give you the mechanical understanding no course provides.

## Project Milestones
🛠️ PROJECT MILESTONES — 6 PROJECTS IN 26 WEEKS
# | Project | Target Week | Stack | Key Metric | GitHub / Deploy | Status | Notes
1 | Multi-turn Chatbot | Week 4 | React + FastAPI + AsyncOpenAI + SSE + Railway | Streaming latency < 500ms, session memory 20 turns | P1: Live Railway URL | Not Started | First public project. Blog post announcing it = Week 5 LinkedIn content.
2 | Document Q&A RAG App | Week 8 | FastAPI + LangChain LCEL + Pinecone + PyMuPDF + RAGAS | RAGAS faithfulness > 0.85, citation accuracy > 90% | P2: Live URL + RAGAS score in README | Not Started | Build 20-question test set BEFORE building the pipeline (TDD for AI).
3 | Test Generator Agent | Week 13 | LangGraph + PyGitHub + Python ast + Claude Sonnet + subprocess | Valid test generation rate > 70% across 20 repos | P3: GitHub repo with working PR automation | Not Started | Retry guard ≤ 3. Filter repos > 10k lines. Intel background makes this credible.
4 | LoRA Fine-tuned Model | Week 14 | QLoRA + Unsloth + HuggingFace Hub + PEFT | Perplexity vs base model, task-specific eval score | P3b: HuggingFace Hub model + model card | Not Started | Fine-tune on domain-specific data (code comments, test descriptions).
5 | AI Coding Assistant (Capstone) | Week 22 | tree-sitter + voyage-code-2 + Claude Sonnet + FastAPI + Click/Rich + VS Code ext | P95 review latency < 3s, precision > 0.75 on 50-case eval harness | P4: PyPI + VS Code Marketplace + HF Space | Not Started | Niche: Code Reviewer CLI + VS Code extension sharing one FastAPI backend.
6 | Portfolio README + GitHub | Week 22 | GitHub Profile README + pinned repos + stats widget | 5 pinned repos with live URLs, GIFs, eval metrics | github.com/sushanthk-262 | Not Started | Pin order: Coding Assistant → RAG → Agent → Chatbot → Federated Learning → LeetCode

## 6-Month Overview
📊 6-MONTH PHASE OVERVIEW
Phase | Weeks | Focus | Projects | Course Used | Exit Milestone
Phase 1: Foundation | 1–4 | Transformer theory → LLM APIs → Prompt Eng → FastAPI → HuggingFace | P1: Multi-turn Chatbot (live Railway URL) | Ed Donner Udemy Wks 1-4 + HF Transformers Course | Chatbot live, streaming working, first LinkedIn build-log post
Phase 2: RAG | 5–10 | Embeddings → Vector DBs → RAG pipelines → LangChain LCEL → LlamaIndex → Evals | P2: Document Q&A RAG App (RAGAS score in README) | Ed Donner Udemy Wks 5-9 + OSS PR #1 | RAG app deployed, RAGAS faithfulness > 0.85, first OSS contribution merged
Phase 3: Agents | 11–16 | Agent patterns → LangGraph → Multi-agent → LoRA/QLoRA → Resume → OSS | P3: Test Generator Agent + P3b: LoRA model on HF Hub | LangGraph Udemy Course Wks 11-13 + Ed Donner fine-tuning Wk 14 | Agent auto-opens GitHub PRs, model on HF Hub, resume updated, 10 apps sent
Phase 4: Capstone | 17–22 | tree-sitter → Code embeddings → CLI → VS Code extension → Eval harness → Ship | P4: AI Coding Assistant (PyPI + VS Code + HF Space) + P5: GitHub portfolio | No course — original build. Reference LangGraph course for patterns. | Capstone live on 3 platforms, 50-case eval green, blog post published
Phase 5: Job Hunt | 23–26 | System design prep → Active applying → Interview execution → Offer evaluation | None — portfolio already complete | No new courses — interview prep only | ✅ Signed offer ≥ ₹24 LPA
KEY TARGETS
Current Salary | ₹18.5 LPA |  | Target at Switch | ≥ ₹24 LPA
Time per week | 8–11 hrs |  | Target 18 months | ₹30–40 LPA
Rule | 30% Learn / 70% Build |  | Start Date | [FILL IN]
DSA Track | 2–3 hrs/week parallel |  | Primary Course | Ed Donner Udemy

## Company Targets
🎯 COMPANY TARGETS
Tier | Company | Role Target | Apply From | Careers URL | Emphasis | Status | Notes
1 | Google DeepMind India | AI/ML Engineer | Week 24 | 🔗 Careers | DSA + Research + Systems | Not Applied | Hardest. Needs strong DSA + published work.
1 | Microsoft AI India | AI Engineer | Week 24 | 🔗 Careers | DSA + Azure AI + RAG | Not Applied | Azure OpenAI team. Azure experience a plus.
1 | Meta AI India | ML Engineer | Week 24 | 🔗 Careers | DSA heavy + PyTorch | Not Applied | Strong DSA gate. Needs LC hard.
1 | Flipkart AI | Applied AI Engineer | Week 22 | 🔗 Careers | RAG + LLM APIs + scale | Not Applied | More practical than FAANG. Good fit.
1 | Swiggy AI | ML/AI Engineer | Week 22 | 🔗 Careers | RAG + recommendations + scale | Not Applied | Strong product AI team.
1 | Amazon AI India | Applied Scientist / SDE | Week 24 | 🔗 Careers | DSA + ML + AWS | Not Applied | Bar raiser process. Needs LC prep.
2 | Sarvam AI | LLM Engineer | Week 15 | 🔗 Careers | LLM + Indian languages + RAG | Not Applied | 🔥 TOP TARGET. Bengaluru-based.
2 | Krutrim AI | AI Engineer | Week 15 | 🔗 Careers | LLM infra + fine-tuning | Not Applied | 🔥 TOP TARGET. Ola AI lab.
2 | Portkey.ai | AI Engineer | Week 15 | 🔗 Careers | LLM gateway + RAG + APIs | Not Applied | Small team, high ownership.
2 | Glean | AI Engineer | Week 16 | 🔗 Careers | Enterprise RAG + search | Not Applied | RAG-heavy product. Perfect fit.
2 | Writer AI | LLM Engineer | Week 16 | 🔗 Careers | Fine-tuning + RAG + agents | Not Applied | Enterprise GenAI. Good fit.
2 | Cohere | ML Engineer | Week 18 | 🔗 Careers | Embeddings + RAG + fine-tuning | Not Applied | Model company. Strong embed/RAG needed.
3 | Wellfound AI filter | AI Engineer (various) | Week 14 | 🔗 Careers | Varies by startup | Ongoing | Filter: AI + India + Series A-B
3 | LinkedIn AI filter | AI/ML Engineer | Week 14 | 🔗 Careers | Varies | Ongoing | Set alert: 'AI Engineer Bengaluru'
3 | Otta | AI roles | Week 14 | 🔗 Careers | Varies | Ongoing | Good for startup discovery
3 | Remote.co | Remote AI roles | Week 16 | 🔗 Careers | Varies | Ongoing | For remote-first options

## Visibility Strategy
📣 VISIBILITY STRATEGY — LinkedIn · GitHub · HuggingFace · Discord
Platform | Action | Frequency | Starting When | Goal | Notes
LinkedIn — Build Logs | Post: working demo + 1 key technical decision learned | Weekly | Week 4 (chatbot live) | 500+ connections, inbound recruiter DMs | Hook formula: specific result first. 'Reduced RAG hallucination 40% by...' not 'I learned RAG today'
LinkedIn — Lessons | Post: one thing that surprised you or a comparison (LangChain vs LlamaIndex) | Bi-weekly | Week 6 | Thought leader positioning in Indian AI community | 5 post types: build log / lesson / comparison / OSS contribution / resource share
LinkedIn — Connections | Connect with engineers (not recruiters) at target companies | 5 new/week | Week 6 | Direct referrals at Sarvam/Krutrim/Glean | Comment on their posts first. DM only after 2+ interactions. Never cold-pitch jobs.
GitHub — Profile README | Pin 6 repos: Coding Asst → RAG → Agent → Chatbot → FL → LeetCode | Update on each ship | Week 4 (first pin) | Professional GitHub that sells itself | Every repo: live URL/GIF, eval metrics, architecture diagram. Stats widget on profile.
GitHub — Commits | Daily green squares — even small doc/test commits count | Daily (min 5/week) | Week 1 | Consistent activity graph for recruiters | Commit message quality matters. 'Add RAGAS eval harness for RAG pipeline' > 'update'
HuggingFace | Publish fine-tuned model (Wk 14) + Space demo (Wk 21) + model card | Per milestone | Week 14 + Week 21 | HF profile showing real model work | Model card must include: eval metrics, training data description, limitations.
Discord — LangChain | Answer questions in #help channel on topics you know | 10 min/day | Week 6 | Network with LangChain core team + community | discord.gg/langchain. Never post job-seeking in technical channels.
Discord — HuggingFace | Participate in model release discussions, help with HF API questions | 10 min/day | Week 8 | Visibility with HF team and community | discord.gg/huggingface. Latent Space pod discord also worth joining.
Hackathons | Lablab.ai (Month 3) → HF Sprint (Month 4) → Anthropic/Meta hack (Month 5) | 1 per month | Month 3 | Prizes, network, portfolio pieces, LinkedIn content | 24-hr playbook: working demo by hr 8, polish hr 8-20, submission hr 20-24.
Medium / Dev.to | Technical blog: 'How I built X' — each project = one post | Per project ship | Week 4 | Google SEO traffic, recruiter discovers you | Cross-post to HuggingFace blog for extra reach. Use Carbon.now.sh for code screenshots.
TFUG Bengaluru | Attend meetups, present your project at lightning talk slot | Monthly | Month 2 | Local network, possible referrals to Bengaluru AI startups | TFUG = TensorFlow User Group. Also PyData Bengaluru and IndiaAI community.
Open to Work | Enable 'Open to Work' for RECRUITERS ONLY (not public banner) | Set at Week 22 | Week 22 | Inbound from AI-focused recruiters | Headline format: 'AI/LLM Engineer ¦ RAG · Agents · FastAPI ¦ Intel ¦ Open to Opportunities'